PRODUCTION READINESS AUDIT

BookQuest

Launch decision, material risks, and staged go-live plan

Audit date: 18 July 2026

Audit basis: Repository HEAD b2964f4 and read-only production checks

Assessment: Final technical production-readiness review

Current decision: NO-GO for public paid or institutional production

Permitted mode: Supervised internal or limited beta

EXECUTIVE VERDICT  BookQuest is deployable and live, with a strong automated engineering baseline. It is not yet ready for an unsupervised public, paid, or institutional launch because material identity, privacy, tenancy, upload, and operating controls remain incomplete.

- Proceed only as a supervised beta with restricted users and no institutional commitments.

- Keep payments disabled until provider webhooks, reconciliation, support, and refund controls are operational.

- Reassess only against one exact deployed SHA after the applicable P0 gates are evidenced.

This is a technical readiness audit, not a legal opinion, certification, or penetration test.

# 1. Scope and verified baseline

The review covered application code, route authorization, production configuration, database migrations, CI workflows, recovery evidence, privacy controls, payment behavior, deployment documentation, and read-only checks of the deployed service. No authenticated production mutation, destructive database operation, or penetration test was performed.

| Area | Result | What it proves |
| --- | --- | --- |
| Repository | Clean at b2964f4 | The audited working tree contained no uncommitted changes. |
| GitHub CI | Passed | Typecheck, build, migrations, database tests, and logical restore completed. |
| Security workflow | Passed | The production dependency audit reported zero known vulnerabilities. |
| Local verification | Passed with limitation | Typecheck and build passed; 109 tests ran while 147 database tests were skipped. |
| Live service | Responsive | Public pages returned 200; anonymous /api/me returned 401; HSTS, frame, and MIME protections were present. |
| Deployment provenance | Not fully evidenced | The live service was reachable, but the exact deployed SHA and migration head were not exposed by a release record. |

Evidence: CI run  |  Security run  |  Live capabilities

TEST LIMITATION  The local test command was green but incomplete because no safe TEST_DATABASE_URL was configured. GitHub CI does configure a disposable database, but local production-data isolation still needs to be closed as an operational control.

## Severity and decision rules

- P0 — launch blocker. Close before the launch stage to which the finding applies.

- P1 — required before scale or relied-upon production operation; may be temporarily compensated only with named ownership and expiry.

- P2 — documentation or hardening work that must be scheduled and tracked but is not, by itself, an immediate launch stop.

# 2. P0 launch blockers

## P0  |  Secure account and administrator bootstrap

Observation: The first observed registrant becomes platform administrator through a SELECT COUNT(*) check. Registration immediately starts a 30-day session even when the address has not been verified.

Risk: A public user can claim administration on a fresh deployment, and concurrent first registrations can both observe an empty user table. Unverified identities receive full authenticated access.

Required action: Provision administrators out of band, remove or serialize public bootstrap, keep new accounts pending until verification, mandate administrator MFA, and add a documented takeover-recovery procedure.

Evidence: README admin rule  |  createUser  |  registration session

## P0  |  Close free-AI abuse paths

Observation: Every new account receives three creation credits. Email verification is not checked by requireUser or the upload route, while the audited live capabilities endpoint reported Anthropic generation enabled.

Risk: Attackers can register unowned addresses and spend model credits. Per-IP limits reduce casual abuse but do not cap platform-wide spend or proxy-based account creation.

Required action: Require verified email before credits can be spent; add CAPTCHA or equivalent bot controls, global and account-level budgets, spend alerts, and an emergency AI kill switch.

Evidence: credit grant  |  authentication guard  |  upload route  |  live AI status

## P0  |  Separate production, development, and test data

Observation: The project audit records that local development targeted the production Neon database. The current local environment contains DATABASE_URL but no TEST_DATABASE_URL.

Risk: A developer command, seed script, migration, or future test can modify live customer data. The missing test database also makes local green results incomplete.

Required action: Create isolated Neon development and test branches, rotate the production credential if it remains local, add environment identity assertions, and make destructive scripts refuse production unless an explicit audited override is supplied.

Evidence: existing audit  |  self-hosting warning

# 2. P0 launch blockers — continued

## P0  |  Make privacy erasure and retention enforceable

Observation: Due erasure runs only from a manual maintenance script. Account erasure clears course source_json but leaves extracted source content in source_versions, and it does not check active legal holds before deleting owned content and projections.

Risk: The product's 30-day deletion promise can miss its deadline, private source data can remain after erasure, and institutional hold commitments can be violated.

Required action: Schedule an authenticated, monitored daily job; cover every source table in erasure; enforce legal holds at scheduling and execution; add dry-run reporting, failure alerting, and cross-table deletion tests.

Evidence: privacy promise  |  erasure code  |  maintenance script  |  Vercel cron security

## P0  |  Enforce source confidentiality and outbound network boundaries

Observation: Source access_policy is stored but listing, draft creation, and raw source-document reads rely on broad content capabilities rather than the owner/editors/members policy. Webhook and LTI URLs reject literal private IPs but do not resolve and pin DNS before requests.

Risk: Same-Space members may access proprietary extracted source content beyond its intended policy. Attacker-controlled DNS can redirect outbound integrations toward private network targets.

Required action: Centralize source-read authorization and apply it to listing, authoring, generation, export, and source-document routes. Reuse the DNS resolution, private-range rejection, and address-pinning design already implemented for webpage imports.

Evidence: source listing  |  source draft creation  |  role capabilities  |  webhook URL  |  LTI JWKS

## P0  |  Replace or constrain the hosted upload path

Observation: The route buffers multipart form data before checking a 50 MB application limit and then duplicates the file into an array buffer. PDF and DOCX extraction lacks a total page, archive expansion, extracted-text, and execution-time budget.

Risk: Vercel Functions currently impose a 4.5 MB request-body limit, so the documented 50 MB behavior cannot work reliably in the deployed architecture. Compressed or complex documents can also exhaust memory or processing time.

Required action: Use direct object-storage upload and background extraction, or immediately reduce the advertised limit. Add magic-byte checks, archive/page/text budgets, timeouts, and an isolated extraction worker.

Evidence: upload route  |  extractor  |  Vercel 4.5 MB limit

# 3. Production operations and conditional launch gates

## P0  |  Establish minimum production operations

Observation: The repository has strong CI but no repository-controlled deployment gate, health/readiness route, external error alerting, browser E2E suite, scheduled operational jobs, or SHA-specific post-deploy verification. Migrations can execute lazily on the first live request.

Risk: Failures can remain invisible until an administrator opens the dashboard; slow migrations can block traffic; and rollback or recovery decisions lack objective criteria.

Required action: Add external uptime/error alerts, queue-age alarms, health/readiness endpoints, critical browser E2E tests, explicit pre-traffic migrations, post-deploy smoke checks, rollback criteria, and recurring restore drills against the current schema and production PostgreSQL major version.

Evidence: CI workflow  |  instrumentation  |  lazy migrations  |  deployment guide

## P0  |  Paid launch: make payment fulfillment durable

Observation: Billing completion relies on the browser returning through a GET callback. There is no signed Flutterwave webhook or reconciliation worker, and a transient failed verification can make a transaction terminal before a later valid confirmation.

Risk: Customers can pay without receiving entitlement, while support has no automated reconciliation or refund workflow. BILLING_TEST_MODE=1 can also simulate paid fulfillment in production.

Required action: Before accepting payment, add signed provider webhooks, retryable verification states, scheduled reconciliation, payment failure alerts, refund and support procedures, and a hard production prohibition on simulated billing.

Evidence: billing verification  |  payment callback  |  atomic fulfillment

## P1  |  Publish legal notices and public content governance

Observation: Registration records acceptance of service terms and a privacy notice, but neither is linked or published. Public course publication has no user reporting, moderation queue, copyright/takedown, or abuse-response workflow.

Risk: Consent evidence is weak because the accepted text is unavailable, and the platform lacks a defined response to harmful or infringing public submissions.

Required action: Publish versioned terms and a privacy notice, link them at registration, define operator and subprocessor disclosures, and operationalize reporting, moderation, takedown, appeals, and incident ownership before a broad public launch.

Evidence: registration copy  |  open moderation gate

# 4. Staged go-live decision

Production readiness depends on the intended launch stage. A narrowly supervised beta has a different evidence threshold from paid or institutional production.

| Launch stage | Decision | Minimum closure evidence |
| --- | --- | --- |
| Supervised internal / limited beta | Conditional | Restricted users, no paid launch, no institutional commitments, active manual monitoring, and explicit AI spend supervision. |
| Unsupervised public free launch | NO-GO | Close identity/bootstrap, AI abuse, environment isolation, privacy, source authorization/SSRF, upload, and minimum operations findings; publish legal notices and abuse response. |
| Public paid launch | NO-GO | Meet public-free gate plus signed payment webhooks, reconciliation, alerts, refunds, and support procedures. |
| Institutional launch | NO-GO | Meet public gate plus penetration testing, WCAG 2.2 AA assessment, processor/region approval, real LMS validation, recovery exercise, and partner acceptance. |

REASSESSMENT TRIGGER  Re-run the complete release gate against one exact deployed SHA. Record CI, dependency audit, database migration head, authenticated smoke results, scheduled-job evidence, alert delivery, restore proof, and named acceptance of any residual risk.

## Institutional assurance remains open

- Independent penetration test with material findings closed.

- Full-journey WCAG 2.2 Level AA assessment and remediation record.

- Approved Vercel, Neon, Anthropic, Resend, and Flutterwave data-processing and regional terms as applicable.

- Named LMS launch and recovery/lockout testing with the actual partner configuration.

- Current-schema restore exercise, incident tabletop, and responsible stakeholder acceptance.

Evidence: institutional checklist  |  external gates

# 5. Action plan

## First 30 days — close immediate launch risk

- Replace public first-user administration with a controlled bootstrap and require verified email before generation privileges.

- Add AI bot controls, per-account and platform budgets, spend alerts, and an emergency kill switch.

- Provision isolated development and test databases, rotate credentials where required, and run the complete local database suite safely.

- Implement scheduled privacy maintenance, complete cross-table erasure, and enforce legal holds at scheduling and execution.

- Centralize source authorization and remediate webhook/LTI DNS rebinding and private-network access.

- Select the upload architecture and align the user-visible limit with the hosted path.

- Add health/readiness endpoints, external uptime and error alerts, and authenticated scheduled maintenance jobs.

- Assign an owner, target date, acceptance evidence, and residual-risk decision to every P0 item.

## Days 31–60 — make release repeatable

- Automate browser E2E coverage for registration, verification, upload, generation, publishing, learning, billing, and recovery.

- Run migrations before traffic with a separate owner credential, a restricted runtime role, timeouts, compatibility checks, and rollback criteria.

- Complete a current-schema PITR and restore drill; declare target RPO/RTO and drill cadence.

- If payments are planned, implement signed Flutterwave webhooks, reconciliation, alerts, and refund/support procedures.

- Publish versioned legal notices and establish content reporting, moderation, takedown, and appeals.

- Issue a SHA-specific production evidence pack and obtain sign-off for the intended launch stage.

## Acceptance evidence for each action

- Automated test or executable control demonstrating the requirement.

- Production or production-equivalent observation tied to an exact commit SHA.

- Named owner, review date, and alert or operating procedure where ongoing work is required.

- Documented residual risk and approval if the control is intentionally deferred.

# 6. Documentation corrections and release record

The project has extensive documentation, but the current set is not a reliable production release record. Consolidate it into one maintained release-gate document tied to the exact deployed commit.

- Refresh evidence for migrations 24–25, Deep Reads, the current billing behavior, and the final learner flow.

- Correct README statements that missing payment keys always produce successful simulated purchases.

- Correct the deployment guide: current migrations run under a transaction-scoped advisory lock and all pending migrations share one transaction.

- Update privacy documentation for export schema 10, source_versions retention, summaries, scheduled erasure, and legal-hold behavior.

- Archive or close the stale ad-hoc audit after its environment and secret actions are evidenced.

- Stop describing webhook delivery, reminders, expiry, and erasure as deployed automation until a monitored scheduler exists.

- Complete the cross-release checklist for every production deployment and link each item to evidence.

| Release record field | Required value |
| --- | --- |
| Source | Exact full commit SHA, branch, CI run, security run, and build artifact identifier. |
| Database | Migration head, pre-deploy snapshot, migration result, runtime role, and rollback compatibility. |
| Deployment | Canonical URL, deployment ID, region/config scope, start/end times, and promotion decision. |
| Verification | Authenticated critical-path smoke, scheduled-job proof, alert delivery, dependency audit, and restore evidence. |
| Decision | Launch stage, go/no-go result, approvers, residual risks, compensating controls, and expiry dates. |

## Sign-off

| Role | Decision / name / date |
| --- | --- |
| Engineering |  |
| Security and privacy |  |
| Operations |  |
| Product |  |
| Finance / payments, if applicable |  |
| Institutional partner, if applicable |  |

CURRENT RELEASE DECISION  NO-GO for public paid or institutional production. A supervised internal or limited beta may continue only with restricted users, no paid activation, no institutional claims, and active human monitoring.

## Key external references

Evidence: Vercel request-size guidance  |  Vercel cron operations  |  BookQuest production